## Slide 1
Introduction to Scrum
This document is provided under the international Creative Commons Attribution + Share Alike 4.0 license.
Version 1.1
August 2, 2018
Introduction to Scrum ©2018 TIS INC. Creative Commons License (International Attribution + Share Alike 4.0)

## Slide 2
Why Scrum is needed

## Slide 3
Changes in business environments
In the age when anything released would sell, the structure was simple: it was a matter of how much can be invested and how much can be made.
A few bugs were not an issue, as the product would still sell.
We are now dealing with an uncertain market, where we cannot be sure what will sell. No matter how much we invest, we cannot be sure that we will get a return on that investment. Business models are becoming increasingly short-lived.
Competed on price
Competing on added value
Predictable
Difficult to predict
We need to keep up with rapid changes in the market.

## Slide 4
Definition of Scrum
Scrum is a framework within which people can address complex adaptive problems, while productively and creatively delivering products of the highest possible value.
Lightweight
Easy to understand
Difficult to master
Characteristics
Only 19 roles and rules.
PMBOK V6 has 49 processes.
Scrum is experience-based.
Team members learn by making judgments based on practical experience and existing knowledge.
https://www.scrumguides.org/scrum-guide.html
The rules for Scrum can be found in the Scrum Guide at the URL below.

## Slide 5
Agile, Scrum and Waterfall

## Slide 6
Agile
Being agile means navigating a situation quickly and skillfully.
It is not just a practice but a way of being.
Don’t do agile, be agile
❞
❝
It is important to see agile development not as a purpose in itself but as the manner in which you approach your development.
The core principles can be summed up as the Agile Manifesto and the principles behind it.

## Slide 7
Manifesto for Agile Software Development
In 2001, 17 prominent figures in what was then known as lightweight software development came together to integrate their areas of focus and document the result.
The six who are best known in Japan are:
• Kent Beck (creator of XP and JUnit)
• Martin Fowler (writer of PoEAA, coined the term “microservice”)
• Dave Thomas (author of books such as The Pragmatic Programmer. “Uncle Bob”.)
• Robert C. Martin (Author of Clean Code, Clean Coder, etc.)
• Ken Schwaber (creator of Scrum)
• Jeff Sutherland (creator of Scrum)
Notes: They met at a ski resort in Utah, USA.

## Slide 8
Manifesto for Agile Software Development
http://agilemanifesto.org
We are uncovering better ways of developing
software by doing it and helping others do it.
Through this work we have come to value:
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.
© 2001, the above authors
This declaration may be freely copied in any form,
but only in its entirety through this notice.
Kent Beck Mike Beedle Arie van Bennekum Alistair Cockburn Ward Cunningham Martin Fowler | James Grenning Jim Highsmith Andrew Hunt Ron Jeffries Jon Kern Brian Marick | Robert C. Martin Steve Mellor Ken Schwaber Jeff Sutherland Dave Thomas

## Slide 9
Principles behind the Agile Manifesto
We follow these principles:
Our highest priority is to satisfy the customer
through early and continuous delivery of valuable software.
Welcome changing requirements, even late in development.
Agile processes harness change for the customer's competitive advantage.
Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale.
Business people and developers must work
together daily throughout the project.
Build projects around motivated individuals.
Give them the environment and support they need
and trust them to get the job done.
The most efficient and effective method of conveying information to
and within a development team is face-to-face conversation.
http://agilemanifesto.org/principles.html

## Slide 10
Principles behind the Agile Manifesto (continued)
Working software is the primary measure of progress.
Agile processes promote sustainable development.
The sponsors, developers, and users should be able to maintain a constant pace indefinitely.
Continuous attention to technical excellence
and good design enhances agility.
Simplicity— the art of maximizing the amount
of work not done—is essential.
The best architectures, requirements, and designs
emerge from self-organizing teams.
At regular intervals, the team reflects on how to become
more effective,
then tunes and adjusts its behavior accordingly.
http://agilemanifesto.org/principles.html

## Slide 11
The waterfall process
Definitions of requirements
External design
Internal design
Implementation and unit testing
Integration testing
System testing
Acceptance testing
The familiar V-Model development process

## Slide 12
Differences in process between agile development and waterfall model
Definitions of requirements
Implementation
Testing
Time
Design
Waterfall model
Agile development
Design
Implementation
Testing
Definitions of requirements
Design
Implementation
Testing
Definitions of requirements
Design
Implementation
Testing
Definitions of requirements
Design
Implementation
Testing
Definitions of requirements

## Slide 13
Differences in process between agile development and waterfall model
Source: Scaling Software Agility
Process | Waterfall model | Agile development
Measurement of success | Whether processes were executed according to plan. Measurement by QCD. | Adapting to change. Customer satisfaction. Greater competitive advantage.
Management | Directive orders Top-down | Servant leadership Flat
Plan | Man-hours estimated by scope. | Man-hours estimated by schedule.
Requirements and design | Requirements identified first. All requirements designed. | Requirements received continuously. Designed at the necessary timing.
Implementation | All functions developed simultaneously. | Functions developed in order of priority.
Testing and QA | Done at end. | Testing done continuously from beginning.

## Slide 14
Relationship between agile and Scrum
Agile
Scrum
XP
Kanban
Lean
Crystal
Scrum is an element of agile.
In addition, Agile includes Kanban, which follows the flow of Lean, and XP.

## Slide 15
Adoption rate of Scrum in agile
Scrum has a 70% adoption rate including hybrids
VersionOne 12th Annual State of Agile Report
http://stateofagile.versionone.com/

## Slide 16
What is Scrum?

## Slide 17
Origin of Scrum
Scrum itself was announced by Jeff Sutherland and Ken Schwaber in 1995, but it first appeared in The New New Product Development Game, a research paper published by Ikujiro Nonaka and Hirotaka Takeuchi in 1986.
This report likened the approach to development that had emerged in Japan to a scrum in rugby.
Scrum is actually older than agile.
Luke Burgess introduces the ball into the scrum.
https://ja.wikipedia.org/wiki/%E3%83%95%E3%82%A1%E3%82%A4%E3%83%AB:ST_vs_Gloucester_-_Match_-_23.JPG

## Slide 18
Definition of Scrum(reiterated)
Scrum is a framework within which people can address complex adaptive problems, while productively and creatively delivering products of the highest possible value.
Lightweight
Easy to understand
Difficult to master
Characteristics
Only 19 roles and rules.
PMBOK V6 has 49 processes.
Scrum is experience-based.
Team members learn by making judgments based on practical experience and existing knowledge.
https://www.scrumguides.org/scrum-guide.html
The rules for Scrum can be found in the Scrum Guide at the URL below.

## Slide 19
Projects that are unsuitable for Scrum
Projects that are simple
Projects in which a predetermined work is created
Projects whose team life is short
  Techniques and processes will not be developed if the period is shorter than 3 months
Requirement
Techniques
Indeterminate
Refined
Fixed
Uncertain
Simple
Chaos
Territory suited to Scrum

## Slide 20
Theory of Scrum
Scrum is rooted in experience-based (empirical) process control.
Actual experience
Knowledge
Judgment and Action
Using repetitive, gradual methods to optimize predictability
and manage risks
Making and acting on judgment leads to new knowledge
Making and acting on a judgment builds experience

## Slide 21
The three pillars of Scrum
Transparency
  Visible for those responsible for the results.
  Standardizing so that everyone who views the content is on the same page.
Inspect
Frequent inspection of created content and progress to detect changes.
With that said, inspections must not be so frequent that they impede work.
Adapt
If a process is insufficient, adapt its components.
Adapt processes as early as possible to prevent deviation.
The following three elements are needed to achieve experience-based process control.
One of these applies to every event, work and role in a scrum.

## Slide 22
The Five Standards for Value in Scrum
Commitment
Each individual must be committed to achieving the goal of the scrum team.
The focus must not be on finishing at all costs.
Courage
Members of a scrum team must have the courage to do what is right.
They must tackle difficult issues.
Focus
All members of the scrum team must focus on the work in each sprint
and the goal of the project.
Openness
The scrum team and stakeholders must agree to be
open about their work, issues and progress.
Respect
Members of the scrum team must respect each other as skilled,
independent individuals.
To achieve transparency, inspection and adaptation, these five standards for value need to be adopted.

## Slide 23
The 19 rules of Scrum
Development team(7±2)
Scrum master
Daily
scrum
Sprint(1-4weeks)
Daily
scrum
Daily
scrum
Daily
scrum
Daily
scrum
Daily
scrum
Product owner
Sprint backlog
Definition of “done”
Fault list
Product backlog refinement (5～10%)
Transparency
Inspection
Adaptation
Sprint planning:
Part 1
Sprint
retrospective
Sprint review
Product backlog
Deliverable product
Cancellation of sprint
Sprint planning:
Part 2

## Slide 24
The three roles in Scrum

## Slide 25
The three roles in Scrum
Development team(7±2)
Scrum master
Daily
scrum
Sprint(1-4weeks)
Daily
scrum
Daily
scrum
Daily
scrum
Daily
scrum
Daily
scrum
Product owner
Sprint backlog
Definition of “done”
Fault list
Product backlog refinement (5～10%)
Transparency
Inspection
Adaptation
Sprint planning:
Part 1
Sprint
retrospective
Sprint review
Product backlog
Deliverable product
Cancellation of sprint
Sprint planning:
Part 2

## Slide 26
Scrum team
Development
team
(7±2)
Scrum master
Product owner
Stakeholders
Work requests and explanations
Support
Support
Deliverables and questions
Responsible for explaining
Requirements
Scrum team
A scrum team comprises a product owner, development team and scrum master.
Scrum teams are self-organized with cross-sectional functions.
The best practices to achieve the goal of the project are decided autonomously by the team.

## Slide 27
Product owner (PO)
Responsible for maximizing the value
of the development team’s work and the product
Decides the release date and content to be released
Sole person responsible for management of product backlog
Decides priority order of product backlog (there can be a committee, but the PO is responsible for the decision)
Work requests to development team (only the PO can request work by the development team)
Acceptance and rejection of work results
Clearly indicates product backlog items (PBIs)
Rearranges PBIs to achieve goal and mission
Optimizes the value of the development team’s work
Makes PBIs visible, transparent and explicit to all team members and indicates the work that the scrum team needs to do next
Ensures that the development team understands the PBIs at the necessary level
Cost perception
Negotiation skill
Ability to explain
Decisiveness
Required skills
Consistency
Strategic thinking
Role
Job

## Slide 28
Development team
Creates something that can be released
Manages the members’ work (considers and decides on best practices)
Responsible for working to improve productivity
Development skill
Autonomous organization
Ability to estimate
Cross-sectional work skills (the collective skills of the members must be sufficient to create the product)
Required skills
Role
Fulfilling promises made during sprint planning
Consistently considering and carrying out actions to improve productivity
Job

## Slide 29
Scrum master
Responsible for understanding and formation of scrums
Supports the product owner
Supports the development team
Explains scrums in a way that can be understood
Considers effective ways to manage product backlog
Facilitates events (as necessary)
Eliminates factors that impede the development team’s progress
Servant leadership
Teaching
Facilitation
Coaching
Required skills
Role
Job
Understanding of processes other than Scrum
Understanding of group psychology
Expressing facts (figures)

## Slide 30
Scrum team anti-pattern:
Scrum master in multiple roles
As a scrum master, sometimes this individual is strict with the development team.But in many cases, the rest of the team is unsure of whether the remarks as a scrum master or member of the development team.
This is particularly problematic in cases where the scrum master has worked as a team leader for conventional development projects, which often results in the individual gaining outstanding technical skills. In cases like this, the individual has to balance their role as a scrum master with work such as architectural judgments, design and develop, which places a large burden on them.
Solution
If the individual is an experienced scrum master, they should train other members of the team so that they can act as scrum masters or develop technical skills that can be relied on, and then step down from the role of scrum master.
If the individual is inexperienced, they should choose a scrum master from the development team and focus on development in their own work.
Issues
Development team(7±2)
Product owner
Scrum master and member of development team

## Slide 31
Scrum team anti-pattern:
PO committee
Development team(7±2)
Product owner committee
As there are multiple product owners, they will not agree on everything, which will confuse the development team.
Clashes may occur in the product owner committee, which will delay judgments.
The development team will not know who to contact with questions about specifications.
Scrum master
Solution
While there can be a committee, there needs to be only one product owner making decisions.
The scrum master should block work requests from parties other than the product owner.
Issues

## Slide 32
Scrum team anti-pattern:
Stakeholders who want to be too involved
If stakeholders get actively involved, they will give the development team advice and information, but this will not be consistent with what the product owner says. They will also directly ask the development team to do work such as investigation work that will be applied to the product backlog.
This will lead to an increasing amount of work and information that the product owner is not aware of, leading to decreases in the velocity of the product and causing tasks that should be prioritized to be put off.
Solution
The scrum master should block direct requests from stakeholders and give explanations that ensure that the product owner’s decisions are heard.
The product owner should collect information from stakeholders and provide them with explanations.
Issue
Development team(7±2)
Stakeholders

## Slide 33
The three items produced by Scrum

## Slide 34
The three items produced by Scrum
Development team(7±2)
Scrum master
Daily
scrum
Sprint(1-4weeks)
Daily
scrum
Daily
scrum
Daily
scrum
Daily
scrum
Daily
scrum
Product owner
Sprint backlog
Definition of “done”
Fault list
Product backlog refinement (5～10%)
Transparency
Inspection
Adaptation
Sprint planning:
Part 1
Sprint
retrospective
Sprint review
Product backlog
Deliverable product
Cancellation of sprint
Sprint planning:
Part 2

## Slide 35
Product backlog
Priority | Story | Estimate
1 | Complete XX as A. | 2
2 | Make YY referenceable in list form as B. | 3
3 | Improve performance of process C | 5
... | ... | ...
100 | Create report as D | 8
A list of everything required for the product, in order of priority.
The only source of information on changes that need to be made in the project.
Each element in the product backlog is called a product backlog item (PBI).
The product backlog is constantly changing according to factors such as the business requirements, market situation and technical changes.
The process of making changes to the details, estimates and order of the PBIs is called product backlog refinement.
The timing of refinements is decided by the scrum team.
Backlog refinement tends to account for 10% or less of the development team’s work.
Estimates are relative. The values can be a Fibonacci sequence, S/M/L or anything that works.
Explicit
Uncertain and vague
Clarify through refinement

## Slide 36
Cone of uncertainty
http://itpro.nikkeibp.co.jp/article/COLUMN/20131001/508039/
This expresses the transition of variance in estimates as the project progresses.
At the beginning, the maximum estimate is 16 times the
minimum.
Uncertainty decreases with each sprint
If a mistake occurs, simply make adjustments early
Project schedule

## Slide 37
Confirmation of progress toward goal
Chart: 
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11
Ideal | 100 | 90 | 80 | 70 | 60 | 50 | 40 | 30 | 20 | 10 | 0
Actual | 100 | 95 | 75 | 70 | 63 | 56 | 38 | 45 | 35 | 20 | 0
Resources such as a release burndown chart can be used to track progress and confirm that the desired content will be released at the desired time. Confirming this during sprint reviews makes it possible to provide the product owner with materials for scope adjustment.
If you know the number of points required for release and the timing that is required, it is possible to tell whether a delay is occurring from one sprint.

## Slide 38
Sprint backlogs
Sprint backlogs are plans used to ensure that the product backlog items selected for a sprint can be submitted as deliverable products.
They are lists of the work that the development team must do to achieve the sprint goals.
They are written in the level of detail that is needed, and may be changed during the sprint.
Only the development team can change the sprint backlog.
Estimates indicate the ideal time.
Tasks should be broken into small units, as this enables more accurate estimation.
At a maximum, tasks should be small enough to be completed within the time allocated for development work in one day.
Story | Task | Estimate
Complete XX as A | UI coding | 3.0h
 | Data model design, changes, entity creation | 3.0h
 | Action coding | 2.0h
Make YY referenceable in list form as B. | UI coding | 4.0h
 | Action coding | 2.0h

## Slide 39
Confirmation of progress of sprints
Chart: 
| Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue
Ideal | 30 | 26.6667 | 23.3333 | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 0
Actual | 30 | 28 | 25 | 25 | 20 | 15 | 8 | 3 | 1 | 0
The work remaining in the sprint backlog is tracked to confirm progress.
The burndown chart is often used to check progress in daily scrums.

## Slide 40
Deliverable products
This term encompasses the products created so far and the product backlog items that have been completed in the current sprint.
Deliverable products must be completed by the end of the sprint.
Products that meet the definition of “done” set by the scrum team are deliverable products.
Parts alone cannot be delivered. Usable items, no matter how small, need to be created.

## Slide 41
Transparency of created items

## Slide 42
Definition of “done”
The definition of “done” indicates the point at which a product is deliverable. This is used to evaluate whether work is completed.
This needs to be done before releasing products.
Done
All sprints are completed
Undone
Not all sprints have been executed
Development
UT
80% coverage or greater
IT
Regression testing
Document creation
• Static analysis
Scenario testing
Load testing
Security testing
Release
It is important to get undone tasks done

## Slide 43
The five events in Scrum

## Slide 44
The five events in Scrum
Development team(7±2)
Scrum master
Daily
scrum
Sprint(1-4weeks)
Daily
scrum
Daily
scrum
Daily
scrum
Daily
scrum
Daily
scrum
Product owner
Sprint backlog
Definition of “done”
Fault list
Product backlog refinement (5～10%)
Transparency
Inspection
Adaptation
Sprint planning:
Part 1
Sprint
retrospective
Sprint review
Product backlog
Deliverable product
Cancellation of sprint
Sprint planning:
Part 2

## Slide 45
Sprint planning
Sprint planning: Part 1
This answers the question “What can be delivered as an additional component of the deliverable product that will be created in the sprint?”
The input consists of the product backlog, latest products and the predicted capacity and previous record of the development team.
This is used to determine the number of product backlog items to be selected. The development team is responsible for deciding on the number of items.
After predicting the product backlog that can be delivered during the sprint, sprint goals are set.
Sprint goals are objectives for the sprint that need to be achieved by carrying out the tasks in the product backlog.
Time box: 4 hours every 2 weeks
Priority | Story | Estimate
1 | Complete XX as A | 2
2 | Make YY referenceable in list form as B. | 3
3 | Improve performance of process C | 5
... | ... | ...
100 | Create report as D | 8
Select PBIs to be executed
during the sprint

## Slide 46
Sprint planning
Sprint planning: Part 2
This part answers the question “How will we complete the work that is needed in order to deliver this additional component of the deliverable product?”
The product backlog items selected for execution in part 1 are placed in the sprint backlog.
This is when tasks for the first few days of the sprint are broken down to a workable size.
The tasks may also be broken down during the sprint period as necessary.
The product owner helps to clarify the product backlog and make tradeoffs.
If there is too much or too little work after breaking down the tasks, the product owner is consulted to make adjustments.
The development team must be able to explain how the sprint goals will be achieved.
Task | Estimate
UI coding | 3.0h
Data model design, changes, entity creation | 3.0h
Action coding | 2.0h
UI coding | 4.0h
Action coding | 2.0h
Break down into
specific tasks
Story
Complete XX as A
Make YY referenceable in list form as B.

## Slide 47
Sprints
A continuous period of development work with a time box no larger than one month to create a deliverable product.
Sprints comprise sprint planning, daily scrums, development work, sprint reviews and sprint retrospectives.
Time box: Maximum 1 month
Changes that will adversely affect the sprint goals cannot be made
Quality targets must not be lowered
Negotiation between the product owner and development team may become necessary as studying progresses and the scope is clarified.
Note
Cancellation of sprints
Sprints can be canceled before the end of the time box, but only the product owner has the authority to cancel a sprint.
If a sprint is canceled, the completed items from the product backlog are reviewed.
Uncompleted backlog items are returned to the product backlog after a re-estimation.

## Slide 48
Daily scrums
During daily scrums, the work performed after the previous daily scrum is inspected and a plan is made for work to be performed by the next daily scrum.
This is a time to inspect the progress of work from the sprint backlog.
Daily scrums need to be held at the same time and in the same place every day.
Each member of the development team explains the following points during daily scrums.
What they did the previous day to enable the development team to achieve the sprint goals
What they will do on this day to enable the development team to achieve the sprint goals
Issues that they or the development team faced that affected their ability to achieve the sprint goals
If a detailed point is raised during a daily scrum, all or some of the development team meets after the daily scrum to discuss the matter in detail and then adapt and re-plan.
Time box: 15 minutes per day

## Slide 49
Sprint reviews
At the end of the sprint, the addition to the deliverable product is inspected and the product backlog is adapted if necessary.
During sprint reviews, the scrum team and other relevant personnel review the results of the sprint.
The purpose of sprint reviews is not to confirm progress but to elicit feedback and further cooperation.
Sprint reviews include the following:
Time box: 2 hours every 2 weeks
The product owner invites participants
The product owner explains completed and uncompleted PBIs
The development team discusses strong points from the sprint, along with issues that they faced and how they solved them
The development team demonstrates what they have completed and answers questions
The product owner confirms the current product backlog and predicts when it will be completed
The whole group discusses what to do next and uses this as input for the planning of the next sprint
The schedule, budget, performance and market for the next product release is reviewed

## Slide 50
Sprint retrospectives
These are an opportunity for the scrum team to conduct an inspection and create a plan for improvements to be made in the next sprint.
Sprint retrospectives are held after the sprint review, before the planning of the next sprint.
Time box: 1.5 hours every 2 weeks
The sprint is inspected from the perspectives of people, relationships, processes and tools
Strong points and points requiring improvement in future are identified and organized
Improvement measures to be applied in the next sprint are identified
An improvement plan for the scrum team’s work is created
The definition of “done” is adjusted as appropriate
No specific method is required, but KPT is often used.
Information on practical usage of KPT is provided in the Practical Guide to Project Facilitation: Retrospective Guide[1].
Information on other methods is provided in Agile Retrospectives: Making Good Teams Great[2].
[1]: http://objectclub.jp/download/files/pf/RetrospectiveMeetingGuide.pdf (only Japanese)
[2]: http://shop.ohmsha.co.jp/shopdetail/000000001770/

## Slide 51
Meetings and Attendees
Guideline on meeting attendees | Sprint planning: Part 1 | Sprint planning: Part 2 | Daily scrums | Sprint reviews | Sprint retrospectives
Product owner Responsible for maximizing the value of the development team’s work and the product. Responsible for management of product backlog. | A | A[1] | C[2] | A | C[4]
Scrum master Responsible for understanding and formation of scrums. | A | A | C[3] | A | A
Development team Develops the product. Responsible for fulfilling promises made during sprint planning. | A | A | A | A | A
Stakeholders Interested parties such as product users, investors and/or managers | D | B | D | D | B
A:Must attend
B:Cannot attend
C:May attend depending on the context
D:Can attend but does not have speaking rights
Notes: It is just a rough standard.
For example, in the Scrum Guide, the retrospective is for the "Scrum Team". (Not the development team).

## Slide 52
Meetings and Attendees (continued)
[1] Involvement of product owner in sprint planning: Part 2
The product owner does not need to attend sprint planning: Part 2, as this meeting is to discuss practical methods and make a plan to achieve them.
With that said, the product owner must answer questions when needed.
The development team also needs to provide the product owner with an explanation of how they will achieve the sprint goals.
[2] Involvement of product owner in daily scrums
Useful in cases such as those where obstacles for achieving the sprint goals occur frequently and support from the product owner is needed.
[3] Involvement of scrum master in daily scrums
The scrum master asks the development team to hold daily scrums, but the development team itself is responsible for holding them.
At the beginning of a team’s work, the scrum master may also need to ensure that time boxes are met and rules are followed.
The scrum master does not need to be involved if the development team can run daily scrums well by themselves.
[4] Involvement of product owner in sprint retrospectives
Retrospectives are held without the PO if there are issues related to the inspection and improvement of processes that cannot be described freely if the PO is present.

## Slide 53
Scrum and quality

## Slide 54
Quality issues in waterfall
Acceptance testing
Quality is guaranteed by phase gates, but
it is not possible to tell whether the desired
product was created until acceptance testing.
The major risks are at the end.
Definitions of requirements
Implementation
Integration testing
Design
Good
Good
Good
Normal
Bad

## Slide 55
Quality in Scrum
Time
Design
Implementation
Testing
Definition of
requirements
Design
Implementation
Testing
Definition of
requirement
Design
Implementation
Testing
Definition of
requirement
Design
Implementation
Testing
Definition of
requirement
The degree to which the product meets business requirements is confirmed during sprint reviews
Bad
Normal
Good
Good

## Slide 56
The Kano model
Customer satisfaction
Physical performance
Superior performance
Inferior performance
Satisfied
Dissatisfied
Attractive Quality
Must-be Quality
(basic quality)
One-dimensional Quality
(performance)
"I expect it"
"I like it"
"I can tolerate it"
"I dislike it"
Notes: The quality required by customers is divided into three categories: Must-have, Unified quality and Attractiveness
Must-be Quality
  If it is not satisfied, customers are dissatisfied. It is natural for customers to be satisfied
One-dimensional Quality
  If it is not satisfied, customers are dissatisfied. If it is satisfied, customers are satisfied.
Attractive Quality
  Even if it is unsatisfied, customer are not unsatisfied. If it is satisfied, customers are satisfied.

## Slide 57
The Kano model
Customer satisfaction
Physical performance
Superior performance
Inferior performance
Satisfied
Dissatisfied
Throughput, response time, operation rate, etc.
Unique functions
Whether the function works correctly/as expected
Must-have quality is the same as waterfall
Scrum makes it
easy to increase
attractive and
unified quality
"I expect it"
"I like it"
"I can tolerate it"
"I dislike it"
Notes: The quality required by customers is divided into three categories: Must-have, Unified quality and Attractiveness
Must-have
  If it is not satisfied, customers are dissatisfied. It is natural for customers to be satisfied
Unified quality
  If it is not satisfied, customers are dissatisfied. If it is satisfied, customers are satisfied.
Attractiveness
  Even if it is unsatisfied, customer are not unsatisfied. If it is satisfied, customers are satisfied.

## Slide 58
Quality
Cost
Delivery
Scope
QCD + S
Quality： Fixed
Cost： Fixed
Delivery： Fixed
Scope： Adjustable
Notes: ・Quality is fixed in both Waterfall and Scrum, and quality is not to be sacrificed.
・Delivery is basically fixed.
・In the case of waterfall, it is adjusted with a large amount of buffer cost.（In waterfall, the scope is basically fixed）
・In the case of scram, it is adjusted with scope.（The bulk of the cost is labor cost, which should not be easily increased or decreased in the case of Scrum.）

## Slide 59
Automation of testing
Testing is done more frequently than with waterfall, as development is done repeatedly. Automation is essential for purposes such as regression testing of functions added in the previous sprint.
Points such as the types of tests to be
automated are decided by the scrum team,
as these points are dependent on context.
Design
Implementation
Testing
Definition of
requirements
Design
Implementation
Testing
Definition of
requirement
Design
Implementation
Testing
Definition of
requirement
Design
Implementation
Testing
Definition of
requirement
Time

## Slide 60
Continuous integration and delivery
As with testing, automating this is recommended as frequent build and deployment work is required.

## Slide 61
Metrics of Scrum

## Slide 62
Velocity
Completed
stories
Sprint 1
Sprint 2
Sprint 3
Sprint 4
3
1
5
9
2
3
5
1
1
5
5
5
7
10
Velocity is the total of completed story points for one sprint.
It indicates the productivity of the development team.
This is used as a reference when deciding the capacity during sprint planning.
Velocity

## Slide 63
Using velocity
Release points ≦ velocity (expected or performance so far) x remaining sprints
Determining whether a release is behind schedule
Example: 100 ≦ 10 points × 10 sprints → on schedule
100 ≧ 9 points × 10 sprints → behind schedule
Calculating capacity
Capacity = average effective velocity for 5 sprints
The effective velocity is calculated by removing
the first velocity and the maximum and
minimum velocity so far.
If five sprints have not been completed,
the most recent velocity is used for the effective velocity.

## Slide 64
How success is measured in agile projects
VersionOne 12th Annual State of Agile Report
http://stateofagile.versionone.com/

## Slide 65
Common misunderstandings about Scrum and agile

## Slide 66
Scrum is more productive
When making a predetermined item, waterfall is more productive.
Scrum is best suited for complex situations such as those where rapid changes occur and the correct answer can only be determined by gauging the reaction of the market and users. Scrum enables a shorter lead time and faster market release.
Element | Definition | System development
Setup time | The preparation time. | The time required for planning and design
Process time | Processing and operation time | The time required for implementation and delivery
Queue time | The wait time caused by resource restrictions | Time during which a task is not handled as all team members are working
Wait time | The wait time for dependent tasks | Time spent waiting for dependent modules and delivery of items to be tested
Lead time until market release = P + (S + Q + W)

## Slide 67
Resource efficiency and flow efficiency
High
Low
High
Low
Flow efficiency
Resource efficiency
High operation rate
Long lead time
Short lead time
Poor operation rate
Poor operation rate
Long lead time
High operation rate
Short lead time
Notes: productivity＝resource efficiency ? flow efficiency?

## Slide 68
Resource efficiency and flow efficiency
Resource
Resource
Resource
Resource
Resource
Flow unit
Flow unit
Flow unit
Flow unit
Flow unit
Allocate a single resource until it reaches 100% utilization
Maximizing resources to get the most out of flow units
e.g. pair programming
e.g. multitasking

## Slide 69
Resource efficiency and flow efficiency
High
Low
High
Low
Flow efficiency
Resource efficiency
Lean
Scrum
Water
Fall
Chaos

## Slide 70
Scrum is not suited to large-scale projects
Suited to development in teams of 2-8
One scrum master can manage 1-3 teams
One product backlog and one product owner per product
Same sprint cycle for each team
The LeSS Huge framework can be used for
teams with more than 8 members
This is used for agile frameworks at a
company level.
Retrospectives are held in 8- to 12-week cycles.
There are 5-15 teams (50-125 people) for each
release.
http://www.scaledagileframework.com/
https://less.works/less/homepage?preferred_lang=en

## Slide 71
Documents are not created in Scrum
Scrum values working software over comprehensive documentation, although the necessary documents are, of course, created.
http://agilemanifesto.org/iso/en/manifesto.html

## Slide 72
Scrum produces lower quality than waterfall
The test types and test cases are the same, regardless of the development process, so there is no difference in the basic quality.

## Slide 73
Appendix

## Slide 74
Reasons for adopting agile
To focus more on accelerating software delivery.
VersionOne 12th Annual State of Agile Report
http://stateofagile.versionone.com/

## Slide 75
Benefits of adopting agile
An unexpectedly small number of
respondents cited project cost
reduction.
VersionOne 12th Annual State of Agile Report
http://stateofagile.versionone.com/

## Slide 76
Agile maturity
Cannot be mastered easily
VersionOne 12th Annual State of Agile Report
http://stateofagile.versionone.com/

## Slide 77
Maturity model of configuration and release management
Practice | Build management and continuous integration | Environment and deployment | Release management and compliance | Testing | Data management | Configuration management
Level 3 – Optimization: The focus is on improvement of processes | There is a venue for regular team discussion, which covers points such as integration issues, automation-based solutions, prompt feedback and better visualization. | All environments are well managed. Provisioning is fully automated. Virtualization is used appropriately. | The system operation team and delivery team work together to manage risks and reduce cycle times. | Changes to the full-scale environment are rarely canceled. Any issues are immediately detected and fixed. | Feedback about points such as the database performance and the deployment process itself is received on each release. | Change management policies are constantly verified to confirm that efficient teamwork and prompt deployment are taking place. Checks are also carried out to confirm the auditability of the change management process.
Level 2 – Quantitative management: Processes are measurable and controlled | Build metrics are collected and visualized, and work is conducted accordingly. Builds are not left broken. | Procedures for integrated deployment management and cancellation of releases and re-releases are tested. | The environment is actively managed by monitoring the health of the application. Cycle times are monitored. | Quality metrics and their trends are tracked. Non-functional requirements are defined and measured. | Database updates and rollbacks are tested for each deployment. Database performance is monitored and optimized. | Developers check in on the main line at least once per day. Branches are only used for release work.
Level 1 – Consistent: Automated processes are applied to the entire life cycle of the application | Automated build and test cycles are executed each time a change is committed. Dependency relationships are managed. Scripts and tools are reused. | Software deployment is fully automated and can be completed by simply clicking a button. The same procedure is deployed for all environments. | A process for managing and approving changes is defined and followed. Protocols are followed | Testing such as unit testing and acceptance testing is automated. Acceptance tests are written by the tester. Testing is incorporated into the development process. | Changes to the database are performed automatically as part of the deployment process. | Libraries and dependency relationships are managed. Usage policies for version management systems are defined in the change management process.
Level 0 – Repeatable: Processes are documented and some are automated | Standard builds and tests are automated. All builds can be recreated with an automated procedure using a source management system. | Deployment is automated in some environments. New environments can be created easily. All configuration management information is used externally for version management. | Releases are considered a nuisance, and are infrequent and unreliable. Traceability of release requirements is also limited. | Automated tests are written as part of story development. | An automated script is used to make changes to the database, and the versions of both the script and the application are managed. | Everything that is needed for software creation (source code and settings files, build and deployment script, data migration, etc.) is managed using a version management system.
Level -1 – Frequent regression errors: Processes are not repeatable and management is inadequate. These issues are being addressed. | Software build procedures are manual. Deliverables and build results are not managed. | Software deployment procedures are manual. Binary is environment-dependent. Environment distribution is manual. | Releases are infrequent and unreliable. | Testing is done manually after development. | Data migration is done manually and versions are not managed. | A version management system is not used, or check-ins are rarely done.
Wachi, Yukei; Takagi, Masahiro; translators. Keizokuteki Deribarī: Shinrai Dekiru Sofutowea Rirīsu No Tame No Birudo/Tesuto/Depuroimento No Jidōka
(Continuous Delivery: Reliable Software Releases through Build, Test, and Deployment Automation). Kadokawa/ASCII Media Works, 2012.

## Slide 78
Quick but rough vs. polished but slow
Polished
Rough
Slow
Quick
Speed
Execution
Slow and rough
Polished but slow
Quick but rough
Quick and polished

## Slide 79
Quick but rough vs. polished but slow
Polished
Rough
Quick
Slow
Speed
Execution
Lean
Scrum
Water
Fall
Chaos

## Slide 80
Scaling agile
VersionOne 12th Annual State of Agile Report
http://stateofagile.versionone.com/